## RACI
|  | Roles | Luis | Thomas | Julien
| Task/Deliverable | Status
Phase 1
| Choose Dev/Network Responsible | Done | R | I | I
| Create QrCode | Work | R | R | I
| Prepare Documentation and Charts | Done | R | C | C
| Network Model | Done | I | C | R
Phase 2
| Finish C App |  | R A | R | C
| Progress Web App |  | C | R | C
| History Developpement |  | C | C | R
Phase 3
Web - Reservations
Web - Accounts
Web - Payment Simulation
Web - Receipt Generation
Web - WebGL
Web - Multi - Languages
Detailed Documentation of Mission 2
Dynamic PAT
Functinal ESXi
Phase 4
Partner Management
Bases of the Reservation System
IPSec
Phase 5
"Dossier Complet d'Utilisation logicielle"
Security Audit and Value Proposition(Mission 3)
All Web Files
2 Databases (empty/with data) in Text Format to Import
Java App and C App w/ all Needed Sources
Executable Ready
The End
R | Responsible | Assigned to complete the task or deliverable.
A | Accountable | Has final decision-making authority and accountability for completion. Only 1 per task.
C | Consulted | An advisor, stakeholder or subject matter expert who is consulted before a decision or action is taken.
I | Informed | Must be informed after a decision or action is taken.